## Лист1
ID | Title | Module | Severity | Priority | Precondition | Steps to Reproduce | Expected Result | Actual Result | Status
BUG-001 | Top Places "See All" button does not navigate to list page | Top Places | Medium | Medium | Application is launched. | 1. Open Home/Resorts/Hotels tab. 2. Navigate to Top Places section. 3. Tap "See All". | Top Places list page opens. | Nothing happens after tapping the button. | Open
BUG-002 | Same image is displayed for multiple Top Places | Top Places | Low | Low | Application is launched. | 1. Open any tab. 2. Navigate to Top Places section. 3. Review displayed places. | Each place displays its own corresponding image. | The same image is displayed for multiple places. | Open
BUG-003 | Restaurant reviews are not displayed | Restaurant Details | Low | Medium | Restaurant details page is opened. | 1. Open Restaurants list. 2. Select any restaurant. 3. Scroll to Reviews section. | Reviews are displayed. | Reviews section is empty. | Open
BUG-004 | Resort reviews are not displayed | Resort Details | Low | Medium | Resort details page is opened. | 1. Open Resorts list. 2. Select any resort. 3. Scroll to Reviews section. | Reviews are displayed. | Reviews section is empty. | Open
BUG-005 | Resorts tab is incorrectly labeled as "Restaurants" | Bottom Navigation | Low | Medium | Application is launched. | 1.Open application. 2. Review bottom navigation bar. | Second tab is labeled as "Resorts". | Second tab is labeled as "Restaurants". | Open
BUG-006 | Hotel reviews are not displayed | Hotel Details | Low | Medium | Hotel details page is opened. | 1. Open Hotels list. 2. Select any hotel. 3. Scroll to Reviews section. | Reviews are displayed. | Reviews section is empty. | Open
BUG-007 | Hotel names are truncated in Hotels list | Hotels List | Low | Low | Hotels list page is opened. | 1. Open Hotels list. 2. Review hotel names. | Full hotel names are displayed. | Hotel names are truncated (e.g., "Renion...", "Kazakh...", "Garden..."). | Open
BUG-008 | Placeholder text "Label" is displayed on Hotel Details page | Hotel Details | Low | Medium | Hotel details page is opened. | 1. Open Hotels list. 2. Select hotel "Kazakhstan". 3. Review information under hotel name. | Meaningful information such as rating, category, or hotel type is displayed. | Placeholder text "Label" is displayed. | Open